## Important Information
Group No. 5 |  |  |  |  | 2024-12-14
Link: | Description: | Use: | בוצע? | שם מטלה | תאריך הגשה | הערות | דחיפות (ימים נותרו להגשה)
https://github.com/KoganTheDev/BLib_MidTerm_Project.git | Main repository GitHub page | Version Control Note: This file and UML diagrams are passed using the git repository. | FALSE
Team Roles | Link to worksheet in this file. | Specifies roles for each team member. | FALSE | מטלה 2 שיטות (ממורקר) | 2024-12-24 | חלוקת עבודה (לשונית Task2 - Engineering Methods) | 10
Meeting Schedule | Link to worksheet in this file. | Handle a meeting schedule to use as a reference at the end of the mid-term project. | FALSE
Requirements | Link to worksheet in this file. | Specifies the requirements for the library project - "Blib". | FALSE
Acceptance Testing | Link to worksheet in this file. | Specifies the Acceptence Testing needed for the library project - "Blib". | FALSE
Code Standards | Link to worksheet in this file. | Specifies how to write each type of element in the code. E.g CamelCase, kabab-case, Uppercase. | FALSE
FALSE
FALSE
| Useful links |  | FALSE
פרויקט אמצע תואר חלק א.pdf | מכיל תיאור על הפעולות והמשימות שיש לבצע - ממורקר *עדיף להשתמש בלשונית Requirements במסמך זה כי היא יותר מתומצתת |  | FALSE
https://devdocs.io/ | Containts Documentation on everything a Software Engineer needs. | Documentation | FALSE
https://slidesgo.com/ | Templates for presentations. | Will make creating a presentation if needed, much easier! | FALSE
https://vickysteeves.gitlab.io/collaborating-with-git/collaborating-with-git.html | התנהלות עם GIT כולל Work Flow |  | FALSE

## Task2 - Engineering Methods
משימה | פירוט | זוג מבצע | בוצע? | מי עשה בקרה? | עבר בקרה? | ניקוד במטלה | הערות | מטלה 2 שיטות (ממורקר) | העתק של הקובץ מטלה הממורקר לשם נוחות
|  | חלק 1: UML (65 נקודות) | [5 empty] | פרויקט אמצע תואר חלק א.pdf | העתק ש הקישור מהדף הראשי באקסל לשם נוחות
Activity Diagram חלק 1 | בניית Activity diagram עם Swimlanes. * דיאגרמה אחת ל"השאלת ספר" (כולל אופציה להארכה והחזרה) | יניב + אלמוג | FALSE |  | FALSE | 18 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | קישור | הסבר
Activity Diagram חלק 2 | בניית Activity diagram עם Swimlanes. * דיאגרמה שנייה הל-"יצירת וצפיית בדו"ח סטטוס מנויים" | יובל + ליאור | TRUE |  | FALSE |  | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | UML Diagrams | בקובץ הזה שמים את הדיאגרמות השונות נמצא במחסן הפרויקט ב-GITHUB Blib->UML->G5_Assignment2
Class Diagram | תיאור מבנה מערכת התוכנה + שימוש ב תבנית ECB( Pattern ECB), o יש לפרט מתודות ספציפיות הנכללות במחלקות השונות ) אין צורך לתאר את "הפעולות הבסיסיות"(. o יש לכלול את מחלקות ה- OCSF והקשר/הממשק אליהן, וכן ייצוג לחבילות הממוחזרות )JavaFX, JDBC )והקשרים אליהם. o יש לכלול תיאור של לפחות Pattern Design אחד הנכלל במערכת. לציין בהערה במודל היכן בדיוק במודל ה-Pattern מתואר - לרשום את הציון כ-Note | ברגע שמסיימים עם ה-Sequence עוברים ל-Class | FALSE |  | FALSE | 30 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | ToDoList | קובץ לניהול תוכנית הפרויקט (מכיל גם את הרשימת משימות ממטלה 1 בפנים)
Sequence Diagram חלק 1 | o תהליך השאלת ספר )כולל אופציה להארכה והחזרה( | יניב + אלמוג | FALSE |  | FALSE | 12 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | Sprint Backlog | מסמך SprintBacklog (שורה 17 באקסל)
Sequence Diagram חלק 2 | ▪ יצירת וצפיית דו"חות סטטיסטיות קשורות להשוואה בין סטוס מנויים בתאריכים שונים | יובל + ליאור | TRUE |  | FALSE |  | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | קבצי JAR של JAVA - דרך המחסן GITHUB עובדים על הקוד
Package | יש לכלול תיאור ארכיטקטורת התוכנה באמצעות Diagram Package. o במידת הצורך – השלמה עצמית של לימוד הנושא ב עזרת Google: לחפש: guidelines diagram Package, ולהשתמש בהגדרות והדוגמאות ב- .Lucidchart-ב או Visual Paradigm במטלה 3 תוערך איכות מודל זה מול מימוש ה- Packages בקוד והתיעוד שלהם . | רון | TRUE | יובל | FALSE | 5 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה
|  | חלק 2: אב טיפוס (25 נקודות) | [5 empty] | 10 | זמן נותר להגשה (בימים)
אב טיפוס שרת (Server) | .1 שרת )server )בסיסי שמתחבר ל - database שלדי שכולל את טבלה אחת הקשורה למערכת |  | FALSE |  | FALSE | 25
אב טיפוס לקוח (Client) | .2 לקוח )client )רץ )במחשב נפרד מהשרת ( מול השרת ופועל מול ה -database . .3 פעולות נדרשות למימוש ב אב-טיפוס : לקרוא באמצעות תוכנת ה-client נתונים מ הטבלה שנמצאת ב- DB שמותקן ב-server, וכן לכתוב )באמצעות ה-client )נתונים אחרים בטבלה זו. |  | FALSE |  | FALSE
| אופן הפעלת האב -טיפוס: o יש להכין מראש )ישירות ב -DB, לא ע"י האב-טיפוס( טבלה בשם "Subscriber ", ובה שמורים פרטי המידע הקשורים למנוי בספריה : subscriber_id (int PK) .1 subscriber_name(string) .2 מפתח )detailed_subscription_history( int FK) .3 לטבלה בלבד – אין צורך במימוש בשלב זה( subscriber_phone_number (string) .4 subscriber_email(string) |  | FALSE |  | FALSE
GUI שרת | • באמצעות הserver, יש להראות את פרטי הקישוריות הרשתית של ה-client המחובר )כתובת IP ושם host), וסטאטוס החיבור. |  | FALSE |  | FALSE
Gui לקוח | • באמצעות ה -client, יש לגשת לפרטים השמורים בטבלה ולהציג את אותם במסך. • באמצעות ה -client, יש לכתוב ערך חדש )update )בשדות: .subscriber_email ו subscriber_phone_number |  | FALSE |  | FALSE |  | o יש לוודא באמצעות גישה ישירה ל -DB( לא ע"י קריאה באמצעות האב -טיפוס( שהערך החדש שנכתב באמצעות ה- client אכן התעדכן בטבלה.
חלק 3: ToDoList (10 נקודות)
ToDoList | Based on the project planning submitted in assignment 1, present detailed planning of the project schedule on a weekly basis for the period : from the date of submission-1 until the date of submission-2. Planning has to be performed as the planning is done in assignment-1. | יובל | TRUE |  | FALSE | 10
Sprint Backlog | בנוסף יש להגיש בקובץ נפרד את ה-BACKLOG SPRINT עבור הספרינט השני )בין הגשה ראשונה לשנייה(. )כלומר יש להגיש את רשימת המשימות שתכננתם לביצוע בשלב הבנייה של הפרויקט: Log Product). | רון | TRUE | יובל | FALSE

## Team Roles
Full Name | תפקיד 1 - שיטות | תפקיד 2 - שיטות | תפקיד 1 - ממשק אדם - מחשב | Comments
Yuval Kogan | Administrator | Product Owner |  | Yuval will take charge of administrative tasks and oversee the product's development, ensuring that all requirements are met and aligning the project with business goals.
Almog Raz | UI/UX Designer |  |  | Almog is responsible for creating an intuitive and visually appealing user interface, ensuring a seamless user experience.
Yaniv Bodaga | Project Logistics Manager |  |  | Yaniv is responsible for overseeing the planning, coordination, and execution of all logistical aspects of the project.
Daniel Lachmakov | Lecturer Coordinator |  |  | Daniel is also responsible to keeping the teem`s mental health in check as well as managing inter-personal conflicts.
Ron Salama | Assignment Coordinator | Scrum master |  | Ron will oversee and manage the submission of all assignments and tasks, ensuring deadlines are met and deliverables are properly submitted on time.
Lior Dagash | Coding Standards Overseer |  |  | Lior is responsible for maintaining high standards in code quality, naming conventions, and documentation.
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: משוך נתונים על החברי צוות ותפקידים

## Meeting Schedule
תאריך פגישה | מטרת הפגישה | הערות
2024-11-21 | עבודה על המטלה של שיטות הנדסיות בנוגע למסמך הסכמות
2024-11-23 | עבודה על מטלה של שיטות הנדסיות.
2024-11-26 | עבודה על המטלה של שיטות הנדסיות + מטלה של ממשק אדם מחשב.
2024-11-28 | המשך עבודה על מטלה של שיטות הנדסיות 1 - סיימנו ToDoList וגם מסמך Scrum Management
2024-11-29 | המשך עבודה על שיטות הנדסיות - סעיף על Use Case סגירת קצוות.
2024-12-02 | עבודה על גיט בחצי צוות
2024-12-04 | עבודה על גיט בחצי צוות
2024-12-09 | מפגש סדנה עם ג'וליה בנוגע למטלה 1 של ממשק אדם - מחשב + מפגש תיקון על המטלה
2024-12-10 | התחלת עבודה על מטלה 2 - שיטות הנדסיות, התחלת עבודה על UML
2024-12-12 | המשך עבודה על מטלה 2 של שיטות, המשך UML, התחלת בקרה על המטלה
2024-12-13 | סיום Sequence ו- Activity
2024-12-14 | ביצוע בקרה על ה-UML השונים
2024-12-17
2024-12-24
2024-12-31
2025-01-07
2025-01-14
2025-01-21
2025-01-28

## Code Standards
Category | Specification | Details
General Naming Conventions | Classes | UpperCamelCase (e.g., MyClass)
General Naming Conventions | Methods | lowerCamelCase (e.g., calculateTotal)
General Naming Conventions | Variables | lowerCamelCase (e.g., itemCount)
General Naming Conventions | Constants | UPPER_SNAKE_CASE (e.g., MAX_CAPACITY)
General Naming Conventions | Packages | lower_case (e.g., com.example.project)
General Naming Conventions | Interfaces | UpperCamelCase (e.g., Runnable)
Object-Oriented Design Principles | Encapsulation | Keep instance variables private, use getters/setters
Object-Oriented Design Principles | Inheritance | Use inheritance for common behavior
Object-Oriented Design Principles | Polymorphism | Leverage interfaces and abstract classes
Object-Oriented Design Principles | SOLID Principles | Follow Single Responsibility, Open/Closed, etc.
Object-Oriented Design Principles | Immutable Objects | Prefer immutability using 'final'
Coding Practices | Avoid Magic Numbers and Strings | Use constants or enums
Coding Practices | Use Streams and Lambdas | Use modern Java features for concise code
Coding Practices | Logging | Use logging frameworks like SLF4J
Coding Practices | Error Handling | Use custom exceptions for specific errors
Coding Practices | Efficient Data Structures | Choose appropriate collections (e.g., HashMap)
Coding Practices | Minimize Synchronization | Synchronize only when necessary
Dependency Management | Use Maven or Gradle | Use a build tool to manage dependencies
Dependency Management | Avoid Overlapping Dependencies | Avoid conflicting versions in dependency trees
Dependency Management | Regularly Review Dependency Trees | Regularly review and update dependencies
Performance and Optimization | Efficient Data Structures | Optimize collection use
Performance and Optimization | Minimize Synchronization | Avoid unnecessary synchronization
Performance and Optimization | Lazy Loading | Load resources when needed
Performance and Optimization | Profiling Tools | Use tools like VisualVM
Security Practices | Input Validation | Validate user inputs
Security Practices | Encryption | Use libraries for password encryption (e.g., Bcrypt)
Security Practices | Avoid Hardcoding Credentials | Use environment variables for credentials
Security Practices | Secure Dependencies | Update dependencies to avoid vulnerabilities
Code Reviews and Collaboration | Pull Requests | Require code reviews before merging
Code Reviews and Collaboration | Static Code Analysis | Use tools like SonarQube for static analysis
Code Reviews and Collaboration | Version Control Branching | Descriptive branch names (e.g., feature/login)
Code Reviews and Collaboration | Commit Messages | Meaningful commit messages (e.g., Fix: Resolve issue)
Documentation and README | API Documentation | Generate documentation with Javadoc or Swagger
Documentation and README | README Essentials | README should include project overview, usage, etc.
Testing Coverage | Unit Tests | Test edge cases and null checks
Testing Coverage | Integration Tests | Test API/component interactions
Testing Coverage | Code Coverage Tools | Use tools like JaCoCo for coverage measurement

## Requirements
Req. Number | Requirement Description | Req. Type (FR/NFR) | comments | Done?
| Managing Users |  |  | FALSE
1 | Readers register to the library using the Librarian | NFR |  | FALSE
2 | After Being registered Readers will be called Subsribers | NFR |  | FALSE
3 | The system stores information in a Data Base. | FR |  | FALSE
4 | Information saved for each subsriber is: Personal Information, Subsriber No., Username, Phone Number and Email as well as the user`s History of actions including Overdue books, Losing a book. | NFR |  | FALSE
5 | The System can scan Membership Cards. | FR |  | FALSE
6 | Every Subscriber has a Membership Card that belongs to them | NFR |  | FALSE
7 | The System can identify a Subscriber`s Membership card | FR |  | FALSE
| Searching |  |  | FALSE
8 | The System allows searching Books | FR
9 | Searches are filtered through the next possible filters: Book Name, Book Subject, General Description of the Subject the Reader is looking for. | NFR |  | FALSE
10 | If there`s an available copy of the Book for borrowin of the Subscriber looked for in the Library -> the System will show the Book`s place on the shelf in the Library and that the book is available for borrowing. | FR |  | FALSE
11 | If there`s No available copy of the book availble for borrowing -> the System will show the Subscriber the next date in which the book is supposed to be back on the shelf of the Library. | FR |  | FALSE
12 | A Reader can connect to a POS (point of sale) or from home to connect the Library`s website. | NFR |  | FALSE
| Borrowing |  |  | FALSE
13 | The Librarian excutes the borrowing process. | NFR |  | FALSE
14 | The book MUST be in the library in order to be borrowed. | NFR |  | FALSE
15 | The System can read Bar codes. | FR |  | FALSE
16 | When borrowing a book it`s possible to scan a Barcode and then the user`s ID, borrowing date and Library book due date are recorded. | NFR |  | FALSE
17 | Books due date is given mostly for up to two weeks. | NFR |  | FALSE
18 | The system can send SMS massages. | FR |  | FALSE
19 | The system can send Email massages | FR |  | FALSE
20 | SMS and Email both will be sent one day before the book`s due date. | NFR |  | FALSE
21 | A subscriber can ask an extention for the book`s due date. | NFR |  | FALSE
22 | Request for a due date extension can be sent a week or less in advance to the due date. | NFR |  | FALSE
23 | The request for extending the book`s due date will be approved only when the book doesn`t have an order waiting to get this book. | NFR |  | FALSE
24 | The system manages requests for extending the book`s due date, either when the request is approved or declined. | FR |  | FALSE
25 | Confirmation of approval or Declining massage will be sent by the system. | NFR |  | FALSE
26 | The system sends an automatic response to the Librarian in case the request is approved. | FR |  | FALSE
27 | Subscriber can ask for an extension to the due date of the book ONLY when their subscription is not Frozen. | NFR |  | FALSE
| Reservation |  |  | FALSE
27 | Subscriber can reserve a book whenever all of the copies of the book are already borrowed. | NFR |  | FALSE
28 | Reservation is done in a manner of "First Come - First Served". | NFR |  | FALSE
29 | The amount of reservations allowed is the same amount of the book`s copies within the library. | NFR | E.g if there are 10 copies in the library (borrowed or not) then 10 reservations are allowed. | FALSE
30 | A subscriber can can reserve as many books as they want. | NFR |  | FALSE
31 | The system sends an Email to the subscriber when a reserved book is in stock. | FR |  | FALSE
32 | A reservation is saved for up to two days after the email of reservation confirmation was sent. | NFR |  | FALSE
33 | If the subscriber doesn`t borrow the reserved book in the given time limit, the reservation is canceled. | NFR |  | FALSE
34 | A subscriber can reserve a book ONLY if their account isn`t Frozen. | NFR |  | FALSE
| Returning a Book |  |  | FALSE
35 | Returning a book is made by the Librarian. | NFR |  | FALSE
36 | If a subscriber is being late returning a book, and the returning date has been exceeded for more than a week -> The user`s membership is FROZEN for a full month | NFR |  | FALSE
37 | Every single action a Subscriber did (other than searching) is being recorded in the Subsriber History. | NFR | IMPORTANT, *Notice that if an action fails it`ll not be recorded. | FALSE
| Managing Information |  |  | FALSE
38 | The system allows a subscriber to see their History. | FR |  | FALSE
39 | The system allows a subscriber to make changes in some of their personal information. | FR |  | FALSE
40 | The information a subscriber can change is: Phone Number & Email. | NFR | Changes in Subscriber number, Status(frozen or not) and borrowing history cannot be changed! | FALSE
41 | The Librarian can see each subscriber`s profile. | NFR |  | FALSE
42 | The Librarian can update the return book`s date (manually) | NFR | Limited by the original returning due date | FALSE
43 | If a Librarian changes a book`s return date`s (manually), The name of the Librarian and update`s date is being recorded. | NFR |  | FALSE
| Analyzing and Viewing Data |  |  | FALSE
44 | The system generates reports | FR | There are two types of reports: 1.Borrowing date report. 2. Subscriber`s status report | FALSE
45 | The reports will be generated by the system every single month. | NFR |  | FALSE
46 | Borrowing date report includes information about book`s borrowing time INCLUDING overdue of returning a book by its date. | NFR | Must be done as a Graph. | FALSE
47 | Subscriber`s status report includes Subscriber`s status throughout the month. | NFR | Must be done as a Graph. (A Gantt graph might be a good choice here.) | FALSE
48 | The reports are shown visually in graph. (Such as Gantt chart) | NFR |  | FALSE
49 | Possible Subscriber`s status are Frozen\not Fronzen. | NFR |  | FALSE

## Acceptance Testing
Searching
Test ID | Description | Expected Result | Precondition | Comments
SearchSuccessfulFilterBookName | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fang". Press Enter. | Opens a page that contains information about the book. | The book is in the library.
SearchSuccessfulFilterBookSubject | Click on search bar. Click on Book Subject tab. Type a Book Subject: "Adventure". Press Enter. | Opens a page that contains information about the book. | The book is in the library.
SearchSuccessfulFilterGeneralDescriptionOfSubject | Click on search bar. Click on General Subject Description tab. Type a General Subject Description: "An adventure book is a thrilling genre that takes readers on exciting journeys filled with challenges, exploration, and unexpected twists. It often features courageous characters, exotic settings, and high-stakes quests that ignite the spirit of discovery and resilience." Press Enter. | Opens a page that contains information about books of the same subject. | The book is in the library.
SearchEmptyString | Click on Search bar. Press Enter | Send an alert and open a window that states that the user must enter values to search using the library`s system. | -
UserCancelsTheOperation | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fang". Press "Cancel". | The system clears the fields. |  | The user has to enter at least one character to run the test.
SearchFailsThisBookNotInLibrary | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fan". Press"Enter". | Opens a page that states that no page was found. | The book must not be in the library.
SearchFailsFilterBookName | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fan". Press Enter. | Opens a page that states that no page was found. | The book must not be in the library. | The book name has to be misspelled
SearchFailsFilterBookSubject | Click on search bar. Click on Book Name tab. Type a Book Name: "Adventure". Press Enter. | Opens a page that states that no page was found. | The name of the subject is not a name of a real subject. | The subject has to be misspelled.
SearchFailsFilterGeneralDescriptionOfSubject | Click on search bar. Click on General Subject Description tab. Type a General Subject Description:"Foo" Press Enter. | Opens a page that states that no page was found. | The description doesn`t describe any kind of subject.
| Borrowing |  |  | FALSE
LibrarianExcutesBorrowingProcessSuccessfully | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". |  | The book must be in the library.
LibrarianBorrowingProcessFailsFieldBookName | Click on search bar. Type Book Name: "White Fan". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The book must not be in the library. | The book name has to be misspelled.
LibrarianBorrowingProcessFailsFieldSubscriberNotInDataBase | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "X X". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The Subscriber name is not in the data base. | The Subscriber`s name has to be either wrong or not in the data base.
LibrarianBorrowingProcessFailsFieldSubscriberIDIsWrong | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "000000000". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The ID allocated to the subscriber is not the same ID entered in the form. | ID must not match
LibrarianBorrowingProcessFailsFieldBorrowingDateInThePast | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/1890". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The borrowing date has to be in the past of present day. | At least one day back.
LibrarianBorrowingProcessFailsDueDateInThePast | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/1890". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The return due date has to be in the past of the present day. | At least one day back.
LibrarianBorrowingProcessFailsFormIsEmpty | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Click "OK" | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | - | -
LibrarianBarcodeScanSuccess | Scan Barcode. | Opens a window which states that the book was borrowed ,including the information stated in the borrowing form. | Barcode matches a book that IS in the library. | -
LibrarianBarcodeScanFail | Scan Barcode. | Opens a window that states that scanning the book`s barcode has failed. | barcode has to be off due to some reason.
SendingDueDateSMSSuccess | The system sends a SMS to a subscriber. | A message reminding him the Due Date to return the book is tomorrow. | The date is one day before the Due Date.
SendingDueDateSMSFail | The system fails to send a SMS to a subscriber | Subscriber Does not recieve SMS message | The date is one day before the Due Date.
SendingDueDateEmailSuccess | The system sends an Email to a subscriber. | A message reminding him the Due Date to return the book is tomorrow. | The date is one day before the Due Date.
SendingDueDateEmailFail | The system fails to send an Email to a subscriber | Subscriber Does not recieve an Email message | The date is one day before the Due Date.
SubscriberExtendingDueDateRequstSuccessApproval | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is approved. Sends a massage to the Librarian stating that the book`s due date has extended. | The book has to be borrowed by the subscriber. The subscriber`s current status is NOT frozen. | Request has to be sent a week or less in advance.
SubscriberExtendingDueDateRequstSuccessRejection | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is Denied. | The book has to be borrowed by the subscriber. The subscriber`s current status is frozen. | Request has to be sent a week or less in advance.
SubscriberExtendingDueDateRequestFailsThereIsAnotherReservation | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is denied due to book being reserved already by someone else. | The book has to be borrowed by the subscriber. The subscriber`s current status is frozen. Another Subscriber sent a reservation request for this exact book. | Request has to be sent a week or less in advance. | מה בודקים? • Input תקין • Input שגוי • שגיאות, ערכי קצה וארועים • תנאי קצה • כל מה שיכול להיות לא תקין! • כל מה שיכול להיות פגום!
SubscriberExtendingDueDateRequstFailsToRun | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that stated that the extending request has failed. |  | Request has to be sent a week or less in advance.
Analyzing and Viewing Data
GeneratingSubscriberStatusReportSuccess | The system generates a visually appealing graph that represents the subscriber`s status throughout the month. | A report is generated in the report section of the system. |  | The report is generated every single month.
GeneratingSubscriberStatusReportFail | The System does NOT generate a visually appealing graph that represents the subscriber`s status throughout the month. | No report has generated In the report section of the system. |  | The report is generated every single month.
GeneratingSubscriberStatusReportFailDueToNoSubscribersInTheDataBase | The System does NOT generate a visually appealing graph that represents the subscriber`s status throughout the month. | No report has generated In the report section of the system. | There are no subscribers in the system`s data base. | The report is generated every single month.
ENTER MORE INFORMATION AS NEEDED