## Important Information
Group No. 5 |  |  |  |  | 2024-12-28
Link: | Description: | Use: | בוצע? | שם מטלה | תאריך הגשה | הערות | דחיפות (ימים נותרו להגשה)
https://github.com/KoganTheDev/BLib_MidTerm_Project.git | Main repository GitHub page | Version Control Note: This file and UML diagrams are passed using the git repository. | TRUE | ממשק אדם-מחשב מטלה 2 | 2025-01-01 | סדנה בתאריך 13/1/24 בשעה: 13:30 | 4
Team Roles | Link to worksheet in this file. | Specifies roles for each team member. | FALSE | שיטות הנדסיות - מטלה 3 (מסמך) | 2025-01-28 | לשונית של מטלה 3 בשיטות הנדסיות | 31
Meeting Schedule | Link to worksheet in this file. | Handle a meeting schedule to use as a reference at the end of the mid-term project. | FALSE
Requirements | Link to worksheet in this file. | Specifies the requirements for the library project - "Blib". | FALSE | מפגש עם מגי ביום שני ה6/1 | 6/1/25 בשעה 19:00 הרצאה עם מגיי על פרזנטציה והכנה לקראת העבשת העבודה בתהליך עבודת צוות. | קישור לזום
Acceptance Testing | Link to worksheet in this file. | Specifies the Acceptence Testing needed for the library project - "Blib". | FALSE | הצגה שלנו בנושא עבודת צוות | 2025-01-19 | הנחיות למטלה ינתנו במפגש הזום | 22
Code Standards | Link to worksheet in this file. | Specifies how to write each type of element in the code. E.g CamelCase, kabab-case, Uppercase. | FALSE
FALSE
FALSE
| Useful links |  | FALSE
פרויקט אמצע תואר חלק א.pdf | מכיל תיאור על הפעולות והמשימות שיש לבצע - ממורקר *עדיף להשתמש בלשונית Requirements במסמך זה כי היא יותר מתומצתת |  | FALSE
https://devdocs.io/ | Containts Documentation on everything a Software Engineer needs. | Documentation | FALSE
https://slidesgo.com/ | Templates for presentations. | Will make creating a presentation if needed, much easier! | FALSE
https://vickysteeves.gitlab.io/collaborating-with-git/collaborating-with-git.html | התנהלות עם GIT כולל Work Flow |  | FALSE

## Task3 - Engineering Methods
פירוט | זוג מבצע | בוצע? | מי עשה בקרה? | עבר בקרה? | הערות | Link | Comments
| חלק 1: מימוש - 88 נקודות |  |  |  |  | שיטות הנדסיות - מטלה 3 (מסמך) | PDF של המטלה
מימוש דרישות לפי המסמך דרישות ב-JAVA | כולם | FALSE |  | FALSE |  | מסמך דרישות | המסמך לפיו הולכים לכתוב את הקוד של BLIB
מימוש ארכיטקטורה מבוזרת מבוססת TCP/UP |  | FALSE |  | FALSE |  | Class Diagram | נמצא תחת: Blib/UML/Assignment2
DB רלציוני |  | FALSE |  | FALSE |  | Package Diagram | נמצא תחת: Blib/UML/Assignment3
נדרש שימוש בקריטריוני איכות למבנה, תכן ופעולת התוכנה וממשק המשתמש כפי שנלמדו בהרצאות . |  | FALSE |  | FALSE |  | JavaDoc example | לתת ל-GPT. שילמד איך אתם מתעדים. אחר כך לתת את הקוד שלנו שייצור לכם את התיעוד ורק נשאר לעשות מעבר שהתיעוד תקין ושהוא לא עשה שינויים מעבר לתיעוד
| חלק 2: מבנה ותיעוד (12 נקודות) |  |  |  |  | Test documentation example | לתת ל-GPT. כדי שידע איך לתעד עבורכם את הטסטים שנכתוב.
עליכם להכין את תיעוד המערכת בעזרת מנגנון Javadoc. התיעוד כולל את תיאור מבנה התוכנה ומרכיבי ממשק המשתמש. יש לתאר את המחלקות וכל מרכיביהן. | כולם | FALSE |  | FALSE
Package Diagram - שכולל את ארכיטקטורת התוכנה | יובל + רון | FALSE |  | FALSE

## Meeting Schedule
תאריך פגישה | מטרת הפגישה | הערות
2024-11-21 | עבודה על המטלה של שיטות הנדסיות בנוגע למסמך הסכמות
2024-11-23 | עבודה על מטלה של שיטות הנדסיות.
2024-11-26 | עבודה על המטלה של שיטות הנדסיות + מטלה של ממשק אדם מחשב.
2024-11-28 | המשך עבודה על מטלה של שיטות הנדסיות 1 - סיימנו ToDoList וגם מסמך Scrum Management
2024-11-29 | המשך עבודה על שיטות הנדסיות - סעיף על Use Case סגירת קצוות.
2024-12-02 | עבודה על גיט בחצי צוות
2024-12-04 | עבודה על גיט בחצי צוות
2024-12-09 | מפגש סדנה עם ג'וליה בנוגע למטלה 1 של ממשק אדם - מחשב + מפגש תיקון על המטלה
2024-12-10 | התחלת עבודה על מטלה 2 - שיטות הנדסיות, התחלת עבודה על UML
2024-12-12 | המשך עבודה על מטלה 2 של שיטות, המשך UML, התחלת בקרה על המטלה
2024-12-13 | סיום Sequence ו- Activity
2024-12-14 | ביצוע בקרה על ה-UML השונים
2024-12-17 | המשך עבודה על ה-Prototype
2024-12-24 | סיום עבודה על מטלה 2 של שיטות הנדסיות + התחלת עבודה על ממשק אדם-מחשב מטלה 2
2024-12-26 | סיום עבודה על מטלה 2 UML סופית
2024-12-28 | עבודה על מטלה 2 של ממשק אדם מחשב - יצירת עץ HTA + מעבר אחרון על חלונות האב טיפוס ברמה נמוכה
2024-12-31
2025-01-07
2025-01-14
2025-01-21
2025-01-28

## Team Roles
Full Name | תפקיד 1 - שיטות | תפקיד 2 - שיטות | תפקיד 1 - ממשק אדם - מחשב | Comments
Yuval Kogan | Administrator | Product Owner |  | Yuval will take charge of administrative tasks and oversee the product's development, ensuring that all requirements are met and aligning the project with business goals.
Almog Raz | UI/UX Designer |  |  | Almog is responsible for creating an intuitive and visually appealing user interface, ensuring a seamless user experience.
Yaniv Bodaga | Project Logistics Manager |  |  | Yaniv is responsible for overseeing the planning, coordination, and execution of all logistical aspects of the project.
Daniel Lachmakov | Lecturer Coordinator |  |  | Daniel is also responsible to keeping the team`s mental health in check as well as managing inter-personal conflicts.
Ron Salama | Assignment Coordinator | Scrum master |  | Ron will oversee and manage the submission of all assignments and tasks, ensuring deadlines are met and deliverables are properly submitted on time.
Lior Dagash | Coding Standards Overseer |  |  | Lior is responsible for maintaining high standards in code quality, naming conventions, and documentation.
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: משוך נתונים על החברי צוות ותפקידים

## Requirements
Req. Number | Requirement Description | Req. Type (FR/NFR) | comments | Assigned To? | Branch name | Done?
| Managing Users |  |  |  |  | FALSE
1 | Readers register to the library using the Librarian | NFR |  |  |  | FALSE
2 | After Being registered Readers will be called Subsribers | NFR |  |  |  | FALSE
3 | The system stores information in a Data Base. | FR |  |  |  | FALSE
4 | Information saved for each subsriber is: Personal Information, Subsriber No., Username, Phone Number and Email as well as the user`s History of actions including Overdue books, Losing a book. | NFR |  |  |  | FALSE
5 | The System can scan Membership Cards. | FR |  |  |  | FALSE
6 | Every Subscriber has a Membership Card that belongs to them | NFR |  |  |  | FALSE
7 | The System can identify a Subscriber`s Membership card | FR |  |  |  | FALSE
| Searching |  |  |  |  | FALSE
8 | The System allows searching Books | FR
9 | Searches are filtered through the next possible filters: Book Name, Book Subject, General Description of the Subject the Reader is looking for. | NFR |  |  |  | FALSE
10 | If there`s an available copy of the Book for borrowin of the Subscriber looked for in the Library -> the System will show the Book`s place on the shelf in the Library and that the book is available for borrowing. | FR |  |  |  | FALSE
11 | If there`s No available copy of the book availble for borrowing -> the System will show the Subscriber the next date in which the book is supposed to be back on the shelf of the Library. | FR |  |  |  | FALSE
12 | A Reader can connect to a POS (point of sale) or from home to connect the Library`s website. | NFR |  |  |  | FALSE
| Borrowing |  |  |  |  | FALSE
13 | The Librarian excutes the borrowing process. | NFR |  |  |  | FALSE
14 | The book MUST be in the library in order to be borrowed. | NFR |  |  |  | FALSE
15 | The System can read Bar codes. | FR |  |  |  | FALSE
16 | When borrowing a book it`s possible to scan a Barcode and then the user`s ID, borrowing date and Library book due date are recorded. | NFR |  |  |  | FALSE
17 | Books due date is given mostly for up to two weeks. | NFR |  |  |  | FALSE
18 | The system can send SMS massages. | FR |  |  |  | FALSE
19 | The system can send Email massages | FR |  |  |  | FALSE
20 | SMS and Email both will be sent one day before the book`s due date. | NFR |  |  |  | FALSE
21 | A subscriber can ask an extention for the book`s due date. | NFR |  |  |  | FALSE
22 | Request for a due date extension can be sent a week or less in advance to the due date. | NFR |  |  |  | FALSE
23 | The request for extending the book`s due date will be approved only when the book doesn`t have an order waiting to get this book. | NFR |  |  |  | FALSE
24 | The system manages requests for extending the book`s due date, either when the request is approved or declined. | FR |  |  |  | FALSE
25 | Confirmation of approval or Declining massage will be sent by the system. | NFR |  |  |  | FALSE
26 | The system sends an automatic response to the Librarian in case the request is approved. | FR |  |  |  | FALSE
27 | Subscriber can ask for an extension to the due date of the book ONLY when their subscription is not Frozen. | NFR |  |  |  | FALSE
| Reservation |  |  |  |  | FALSE
27 | Subscriber can reserve a book whenever all of the copies of the book are already borrowed. | NFR |  |  |  | FALSE
28 | Reservation is done in a manner of "First Come - First Served". | NFR |  |  |  | FALSE
29 | The amount of reservations allowed is the same amount of the book`s copies within the library. | NFR | E.g if there are 10 copies in the library (borrowed or not) then 10 reservations are allowed. |  |  | FALSE
30 | A subscriber can can reserve as many books as they want. | NFR |  |  |  | FALSE
31 | The system sends an Email to the subscriber when a reserved book is in stock. | FR |  |  |  | FALSE
32 | A reservation is saved for up to two days after the email of reservation confirmation was sent. | NFR |  |  |  | FALSE
33 | If the subscriber doesn`t borrow the reserved book in the given time limit, the reservation is canceled. | NFR |  |  |  | FALSE
34 | A subscriber can reserve a book ONLY if their account isn`t Frozen. | NFR |  |  |  | FALSE
| Returning a Book |  |  |  |  | FALSE
35 | Returning a book is made by the Librarian. | NFR |  |  |  | FALSE
36 | If a subscriber is being late returning a book, and the returning date has been exceeded for more than a week -> The user`s membership is FROZEN for a full month | NFR |  |  |  | FALSE
37 | Every single action a Subscriber did (other than searching) is being recorded in the Subsriber History. | NFR | IMPORTANT, *Notice that if an action fails it`ll not be recorded. |  |  | FALSE
| Managing Information |  |  |  |  | FALSE
38 | The system allows a subscriber to see their History. | FR |  |  |  | FALSE
39 | The system allows a subscriber to make changes in some of their personal information. | FR |  |  |  | FALSE
40 | The information a subscriber can change is: Phone Number & Email. | NFR | Changes in Subscriber number, Status(frozen or not) and borrowing history cannot be changed! |  |  | FALSE
41 | The Librarian can see each subscriber`s profile. | NFR |  |  |  | FALSE
42 | The Librarian can update the return book`s date (manually) | NFR | Limited by the original returning due date |  |  | FALSE
43 | If a Librarian changes a book`s return date`s (manually), The name of the Librarian and update`s date is being recorded. | NFR |  |  |  | FALSE
| Analyzing and Viewing Data |  |  |  |  | FALSE
44 | The system generates reports | FR | There are two types of reports: 1.Borrowing date report. 2. Subscriber`s status report |  |  | FALSE
45 | The reports will be generated by the system every single month. | NFR |  |  |  | FALSE
46 | Borrowing date report includes information about book`s borrowing time INCLUDING overdue of returning a book by its date. | NFR | Must be done as a Graph. |  |  | FALSE
47 | Subscriber`s status report includes Subscriber`s status throughout the month. | NFR | Must be done as a Graph. (A Gantt graph might be a good choice here.) |  |  | FALSE
48 | The reports are shown visually in graph. (Such as Gantt chart) | NFR |  |  |  | FALSE
49 | Possible Subscriber`s status are Frozen\not Fronzen. | NFR |  |  |  | FALSE

## Tests
Test Name | Test Description | comments | Branch name | Done?
| Managing Users |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
| Searching |  |  | FALSE
The System allows searching Books
| Searches are filtered through the next possible filters: Book Name, Book Subject, General Description of the Subject the Reader is looking for. |  |  | FALSE
| If there`s an available copy of the Book for borrowin of the Subscriber looked for in the Library -> the System will show the Book`s place on the shelf in the Library and that the book is available for borrowing. |  |  | FALSE
| If there`s No available copy of the book availble for borrowing -> the System will show the Subscriber the next date in which the book is supposed to be back on the shelf of the Library. |  |  | FALSE
| A Reader can connect to a POS (point of sale) or from home to connect the Library`s website. |  |  | FALSE
| Borrowing |  |  | FALSE
| The Librarian excutes the borrowing process. |  |  | FALSE
| The book MUST be in the library in order to be borrowed. |  |  | FALSE
| The System can read Bar codes. |  |  | FALSE
| When borrowing a book it`s possible to scan a Barcode and then the user`s ID, borrowing date and Library book due date are recorded. |  |  | FALSE
| Books due date is given mostly for up to two weeks. |  |  | FALSE
| The system can send SMS massages. |  |  | FALSE
| The system can send Email massages |  |  | FALSE
| SMS and Email both will be sent one day before the book`s due date. |  |  | FALSE
| A subscriber can ask an extention for the book`s due date. |  |  | FALSE
| Request for a due date extension can be sent a week or less in advance to the due date. |  |  | FALSE
| The request for extending the book`s due date will be approved only when the book doesn`t have an order waiting to get this book. |  |  | FALSE
| The system manages requests for extending the book`s due date, either when the request is approved or declined. |  |  | FALSE
| Confirmation of approval or Declining massage will be sent by the system. |  |  | FALSE
| The system sends an automatic response to the Librarian in case the request is approved. |  |  | FALSE
| Subscriber can ask for an extension to the due date of the book ONLY when their subscription is not Frozen. |  |  | FALSE
| Reservation |  |  | FALSE
| Subscriber can reserve a book whenever all of the copies of the book are already borrowed. |  |  | FALSE
| Reservation is done in a manner of "First Come - First Served". |  |  | FALSE
| The amount of reservations allowed is the same amount of the book`s copies within the library. | E.g if there are 10 copies in the library (borrowed or not) then 10 reservations are allowed. |  | FALSE
| A subscriber can can reserve as many books as they want. |  |  | FALSE
| The system sends an Email to the subscriber when a reserved book is in stock. |  |  | FALSE
| A reservation is saved for up to two days after the email of reservation confirmation was sent. |  |  | FALSE
| If the subscriber doesn`t borrow the reserved book in the given time limit, the reservation is canceled. |  |  | FALSE
| A subscriber can reserve a book ONLY if their account isn`t Frozen. |  |  | FALSE
| Returning a Book |  |  | FALSE
| Returning a book is made by the Librarian. |  |  | FALSE
| If a subscriber is being late returning a book, and the returning date has been exceeded for more than a week -> The user`s membership is FROZEN for a full month |  |  | FALSE
| Every single action a Subscriber did (other than searching) is being recorded in the Subsriber History. | IMPORTANT, *Notice that if an action fails it`ll not be recorded. |  | FALSE
| Managing Information |  |  | FALSE
| The system allows a subscriber to see their History. |  |  | FALSE
| The system allows a subscriber to make changes in some of their personal information. |  |  | FALSE
| The information a subscriber can change is: Phone Number & Email. | Changes in Subscriber number, Status(frozen or not) and borrowing history cannot be changed! |  | FALSE
| The Librarian can see each subscriber`s profile. |  |  | FALSE
| The Librarian can update the return book`s date (manually) | Limited by the original returning due date |  | FALSE
| If a Librarian changes a book`s return date`s (manually), The name of the Librarian and update`s date is being recorded. |  |  | FALSE
| Analyzing and Viewing Data |  |  | FALSE
| The system generates reports | There are two types of reports: 1.Borrowing date report. 2. Subscriber`s status report |  | FALSE
| The reports will be generated by the system every single month. |  |  | FALSE
| Borrowing date report includes information about book`s borrowing time INCLUDING overdue of returning a book by its date. | Must be done as a Graph. |  | FALSE
| Subscriber`s status report includes Subscriber`s status throughout the month. | Must be done as a Graph. (A Gantt graph might be a good choice here.) |  | FALSE
| The reports are shown visually in graph. (Such as Gantt chart) |  |  | FALSE
| Possible Subscriber`s status are Frozen\not Fronzen. |  |  | FALSE

## Code Standards
Category | Specification | Details
General Naming Conventions | Classes | UpperCamelCase (e.g., MyClass)
General Naming Conventions | Methods | lowerCamelCase (e.g., calculateTotal)
General Naming Conventions | Variables | lowerCamelCase (e.g., itemCount)
General Naming Conventions | Constants | UPPER_SNAKE_CASE (e.g., MAX_CAPACITY)
General Naming Conventions | Packages | lower_case (e.g., com.example.project)
General Naming Conventions | Interfaces | UpperCamelCase (e.g., Runnable)
Object-Oriented Design Principles | Encapsulation | Keep instance variables private, use getters/setters
Object-Oriented Design Principles | Inheritance | Use inheritance for common behavior
Object-Oriented Design Principles | Polymorphism | Leverage interfaces and abstract classes
Object-Oriented Design Principles | SOLID Principles | Follow Single Responsibility, Open/Closed, etc.
Object-Oriented Design Principles | Immutable Objects | Prefer immutability using 'final'
Coding Practices | Avoid Magic Numbers and Strings | Use constants or enums
Coding Practices | Use Streams and Lambdas | Use modern Java features for concise code
Coding Practices | Logging | Use logging frameworks like SLF4J
Coding Practices | Error Handling | Use custom exceptions for specific errors
Coding Practices | Efficient Data Structures | Choose appropriate collections (e.g., HashMap)
Coding Practices | Minimize Synchronization | Synchronize only when necessary
Dependency Management | Use Maven or Gradle | Use a build tool to manage dependencies
Dependency Management | Avoid Overlapping Dependencies | Avoid conflicting versions in dependency trees
Dependency Management | Regularly Review Dependency Trees | Regularly review and update dependencies
Performance and Optimization | Efficient Data Structures | Optimize collection use
Performance and Optimization | Minimize Synchronization | Avoid unnecessary synchronization
Performance and Optimization | Lazy Loading | Load resources when needed
Performance and Optimization | Profiling Tools | Use tools like VisualVM
Security Practices | Input Validation | Validate user inputs
Security Practices | Encryption | Use libraries for password encryption (e.g., Bcrypt)
Security Practices | Avoid Hardcoding Credentials | Use environment variables for credentials
Security Practices | Secure Dependencies | Update dependencies to avoid vulnerabilities
Code Reviews and Collaboration | Pull Requests | Require code reviews before merging
Code Reviews and Collaboration | Static Code Analysis | Use tools like SonarQube for static analysis
Code Reviews and Collaboration | Version Control Branching | Descriptive branch names (e.g., feature/login)
Code Reviews and Collaboration | Commit Messages | Meaningful commit messages (e.g., Fix: Resolve issue)
Documentation and README | API Documentation | Generate documentation with Javadoc or Swagger
Documentation and README | README Essentials | README should include project overview, usage, etc.
Testing Coverage | Unit Tests | Test edge cases and null checks
Testing Coverage | Integration Tests | Test API/component interactions
Testing Coverage | Code Coverage Tools | Use tools like JaCoCo for coverage measurement

## Acceptance Testing
Searching
Test ID | Description | Expected Result | Precondition | Comments
SearchSuccessfulFilterBookName | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fang". Press Enter. | Opens a page that contains information about the book. | The book is in the library.
SearchSuccessfulFilterBookSubject | Click on search bar. Click on Book Subject tab. Type a Book Subject: "Adventure". Press Enter. | Opens a page that contains information about the book. | The book is in the library.
SearchSuccessfulFilterGeneralDescriptionOfSubject | Click on search bar. Click on General Subject Description tab. Type a General Subject Description: "An adventure book is a thrilling genre that takes readers on exciting journeys filled with challenges, exploration, and unexpected twists. It often features courageous characters, exotic settings, and high-stakes quests that ignite the spirit of discovery and resilience." Press Enter. | Opens a page that contains information about books of the same subject. | The book is in the library.
SearchEmptyString | Click on Search bar. Press Enter | Send an alert and open a window that states that the user must enter values to search using the library`s system. | -
UserCancelsTheOperation | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fang". Press "Cancel". | The system clears the fields. |  | The user has to enter at least one character to run the test.
SearchFailsThisBookNotInLibrary | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fan". Press"Enter". | Opens a page that states that no page was found. | The book must not be in the library.
SearchFailsFilterBookName | Click on search bar. Click on Book Name tab. Type a Book Name: "White Fan". Press Enter. | Opens a page that states that no page was found. | The book must not be in the library. | The book name has to be misspelled
SearchFailsFilterBookSubject | Click on search bar. Click on Book Name tab. Type a Book Name: "Adventure". Press Enter. | Opens a page that states that no page was found. | The name of the subject is not a name of a real subject. | The subject has to be misspelled.
SearchFailsFilterGeneralDescriptionOfSubject | Click on search bar. Click on General Subject Description tab. Type a General Subject Description:"Foo" Press Enter. | Opens a page that states that no page was found. | The description doesn`t describe any kind of subject.
| Borrowing |  |  | FALSE
LibrarianExcutesBorrowingProcessSuccessfully | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". |  | The book must be in the library.
LibrarianBorrowingProcessFailsFieldBookName | Click on search bar. Type Book Name: "White Fan". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The book must not be in the library. | The book name has to be misspelled.
LibrarianBorrowingProcessFailsFieldSubscriberNotInDataBase | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "X X". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The Subscriber name is not in the data base. | The Subscriber`s name has to be either wrong or not in the data base.
LibrarianBorrowingProcessFailsFieldSubscriberIDIsWrong | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "000000000". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The ID allocated to the subscriber is not the same ID entered in the form. | ID must not match
LibrarianBorrowingProcessFailsFieldBorrowingDateInThePast | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/1890". Type Due Date: "15/1/25". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The borrowing date has to be in the past of present day. | At least one day back.
LibrarianBorrowingProcessFailsDueDateInThePast | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Type Subscriber Full Name: "Yuval Kogan". Type Subcriber`s ID: "207840042". Type Borrowing Date: "1/1/25". Type Due Date: "15/1/1890". Click "OK". | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | The return due date has to be in the past of the present day. | At least one day back.
LibrarianBorrowingProcessFailsFormIsEmpty | Click on search bar. Type Book Name: "White Fang". Press "Enter". Click "Borrow". Click "OK" | Opens a window indicate that one of the fields is wrong. Highlight the wrong field in the form. | - | -
LibrarianBarcodeScanSuccess | Scan Barcode. | Opens a window which states that the book was borrowed ,including the information stated in the borrowing form. | Barcode matches a book that IS in the library. | -
LibrarianBarcodeScanFail | Scan Barcode. | Opens a window that states that scanning the book`s barcode has failed. | barcode has to be off due to some reason.
SendingDueDateSMSSuccess | The system sends a SMS to a subscriber. | A message reminding him the Due Date to return the book is tomorrow. | The date is one day before the Due Date.
SendingDueDateSMSFail | The system fails to send a SMS to a subscriber | Subscriber Does not recieve SMS message | The date is one day before the Due Date.
SendingDueDateEmailSuccess | The system sends an Email to a subscriber. | A message reminding him the Due Date to return the book is tomorrow. | The date is one day before the Due Date.
SendingDueDateEmailFail | The system fails to send an Email to a subscriber | Subscriber Does not recieve an Email message | The date is one day before the Due Date.
SubscriberExtendingDueDateRequstSuccessApproval | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is approved. Sends a massage to the Librarian stating that the book`s due date has extended. | The book has to be borrowed by the subscriber. The subscriber`s current status is NOT frozen. | Request has to be sent a week or less in advance.
SubscriberExtendingDueDateRequstSuccessRejection | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is Denied. | The book has to be borrowed by the subscriber. The subscriber`s current status is frozen. | Request has to be sent a week or less in advance.
SubscriberExtendingDueDateRequestFailsThereIsAnotherReservation | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that states that extending the book`s due date is denied due to book being reserved already by someone else. | The book has to be borrowed by the subscriber. The subscriber`s current status is frozen. Another Subscriber sent a reservation request for this exact book. | Request has to be sent a week or less in advance. | מה בודקים? • Input תקין • Input שגוי • שגיאות, ערכי קצה וארועים • תנאי קצה • כל מה שיכול להיות לא תקין! • כל מה שיכול להיות פגום!
SubscriberExtendingDueDateRequstFailsToRun | Click "My Borrowed Books". Click on Search Bar. Type "White Fang". Click "Extend Due Date". | Opens a window that stated that the extending request has failed. |  | Request has to be sent a week or less in advance.
Analyzing and Viewing Data
GeneratingSubscriberStatusReportSuccess | The system generates a visually appealing graph that represents the subscriber`s status throughout the month. | A report is generated in the report section of the system. |  | The report is generated every single month.
GeneratingSubscriberStatusReportFail | The System does NOT generate a visually appealing graph that represents the subscriber`s status throughout the month. | No report has generated In the report section of the system. |  | The report is generated every single month.
GeneratingSubscriberStatusReportFailDueToNoSubscribersInTheDataBase | The System does NOT generate a visually appealing graph that represents the subscriber`s status throughout the month. | No report has generated In the report section of the system. | There are no subscribers in the system`s data base. | The report is generated every single month.
ENTER MORE INFORMATION AS NEEDED

## Task2 - Engineering Methods
משימה | פירוט | זוג מבצע | בוצע? | מי עשה בקרה? | עבר בקרה? | ניקוד במטלה | הערות | מטלה 2 שיטות (ממורקר) | העתק של הקובץ מטלה הממורקר לשם נוחות
|  | חלק 1: UML (65 נקודות) | [5 empty] | פרויקט אמצע תואר חלק א.pdf | העתק ש הקישור מהדף הראשי באקסל לשם נוחות
Activity Diagram חלק 1 | בניית Activity diagram עם Swimlanes. * דיאגרמה אחת ל"השאלת ספר" (כולל אופציה להארכה והחזרה) | יניב + אלמוג | TRUE |  | TRUE | 18 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | קישור | הסבר
Activity Diagram חלק 2 | בניית Activity diagram עם Swimlanes. * דיאגרמה שנייה הל-"יצירת וצפיית בדו"ח סטטוס מנויים" | יובל + ליאור | TRUE |  | TRUE |  | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | UML Diagrams | בקובץ הזה שמים את הדיאגרמות השונות נמצא במחסן הפרויקט ב-GITHUB Blib->UML->G5_Assignment2
Class Diagram | תיאור מבנה מערכת התוכנה + שימוש ב תבנית ECB( Pattern ECB), o יש לפרט מתודות ספציפיות הנכללות במחלקות השונות ) אין צורך לתאר את "הפעולות הבסיסיות"(. o יש לכלול את מחלקות ה- OCSF והקשר/הממשק אליהן, וכן ייצוג לחבילות הממוחזרות )JavaFX, JDBC )והקשרים אליהם. o יש לכלול תיאור של לפחות Pattern Design אחד הנכלל במערכת. לציין בהערה במודל היכן בדיוק במודל ה-Pattern מתואר - לרשום את הציון כ-Note | ברגע שמסיימים עם ה-Sequence עוברים ל-Class | TRUE |  | TRUE | 30 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | ToDoList | קובץ לניהול תוכנית הפרויקט (מכיל גם את הרשימת משימות ממטלה 1 בפנים)
Sequence Diagram חלק 1 | o תהליך השאלת ספר )כולל אופציה להארכה והחזרה( | יניב + אלמוג | TRUE |  | TRUE | 12 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | Sprint Backlog | מסמך SprintBacklog (שורה 17 באקסל)
Sequence Diagram חלק 2 | ▪ יצירת וצפיית דו"חות סטטיסטיות קשורות להשוואה בין סטוס מנויים בתאריכים שונים | יובל + ליאור | TRUE |  | TRUE |  | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה | קבצי JAR של JAVA - דרך המחסן GITHUB עובדים על הקוד | נשלח
Package | יש לכלול תיאור ארכיטקטורת התוכנה באמצעות Diagram Package. o במידת הצורך – השלמה עצמית של לימוד הנושא ב עזרת Google: לחפש: guidelines diagram Package, ולהשתמש בהגדרות והדוגמאות ב- .Lucidchart-ב או Visual Paradigm במטלה 3 תוערך איכות מודל זה מול מימוש ה- Packages בקוד והתיעוד שלהם . | רון | TRUE | יובל | TRUE | 5 | * לפי הערה לשים לב: System לא נמצאת באף אחת מהדיאגרמות בפני עצמה
|  | חלק 2: אב טיפוס (25 נקודות) | [5 empty] | 31 | זמן נותר להגשה (בימים)
אב טיפוס שרת (Server) | .1 שרת )server )בסיסי שמתחבר ל - database שלדי שכולל את טבלה אחת הקשורה למערכת |  | TRUE |  | FALSE | 25
אב טיפוס לקוח (Client) | .2 לקוח )client )רץ )במחשב נפרד מהשרת ( מול השרת ופועל מול ה -database . .3 פעולות נדרשות למימוש ב אב-טיפוס : לקרוא באמצעות תוכנת ה-client נתונים מ הטבלה שנמצאת ב- DB שמותקן ב-server, וכן לכתוב )באמצעות ה-client )נתונים אחרים בטבלה זו. |  | TRUE |  | FALSE
| אופן הפעלת האב -טיפוס: o יש להכין מראש )ישירות ב -DB, לא ע"י האב-טיפוס( טבלה בשם "Subscriber ", ובה שמורים פרטי המידע הקשורים למנוי בספריה : subscriber_id (int PK) .1 subscriber_name(string) .2 מפתח )detailed_subscription_history( int FK) .3 לטבלה בלבד – אין צורך במימוש בשלב זה( subscriber_phone_number (string) .4 subscriber_email(string) |  | TRUE |  | FALSE
GUI שרת | • באמצעות הserver, יש להראות את פרטי הקישוריות הרשתית של ה-client המחובר )כתובת IP ושם host), וסטאטוס החיבור. |  | TRUE |  | FALSE
Gui לקוח | • באמצעות ה -client, יש לגשת לפרטים השמורים בטבלה ולהציג את אותם במסך. • באמצעות ה -client, יש לכתוב ערך חדש )update )בשדות: .subscriber_email ו subscriber_phone_number |  | TRUE |  | FALSE |  | o יש לוודא באמצעות גישה ישירה ל -DB( לא ע"י קריאה באמצעות האב -טיפוס( שהערך החדש שנכתב באמצעות ה- client אכן התעדכן בטבלה.
חלק 3: ToDoList (10 נקודות)
ToDoList | Based on the project planning submitted in assignment 1, present detailed planning of the project schedule on a weekly basis for the period : from the date of submission-1 until the date of submission-2. Planning has to be performed as the planning is done in assignment-1. | יובל | TRUE |  | TRUE | 10
Sprint Backlog | בנוסף יש להגיש בקובץ נפרד את ה-BACKLOG SPRINT עבור הספרינט השני )בין הגשה ראשונה לשנייה(. )כלומר יש להגיש את רשימת המשימות שתכננתם לביצוע בשלב הבנייה של הפרויקט: Log Product). | רון | TRUE | יובל | TRUE |  | נשאר להחליט האם לפצל את הקובץ לספרינט 2 בלבד או שלא.
הערות UML: | מה לעשות? | בוצע?
תרשים ACTIVITY השאלת ספר | צריך לפצל ל-3 דיאגרמות שונות תהליך השאלה תהליך החזרה תהליך הארכה | FALSE
ב-Class דיאגרם, חיבור לתיקיה של הJDBC | נשאיר אץ האובייקטים -> בחיבור גנרי לתיקייה. | FALSE
ב-Class היא אמרה שהיא רוצה לראות 2 דברים אבסטרקטיים ו-2 דברים | להכניס ABSTRACT SERVER ו-SERVER UI להכניס ABSTRACT CLIENT ו-CLIENT UI | FALSE
האם לחבר את הJAVAFX רק לDB? | ???? | FALSE
האם SERVER SERVICE יורש ממישהו? יכול להיות שחסרים CLASS-ים | לעשות בדיקה בקוד ולגזור מסקנות | FALSE
להוסיף את ECHO SERVER שמחובר לJAVAFX | - | FALSE
להכניס את ה-Class של ConnectToDB | - | FALSE
לעשות התאמה יסודית בין האבטיפוס לתרשים מחלקות | כן! | FALSE
FALSE
בסקראם להכניס רק את חלק 2 למטלה |  | FALSE
! השוואה אחרונה על הכל ושגר ושכח |  | FALSE
הערות טיראן | מה לעשות? | בוצע? | תשובות
להראות IP דרך ה-GUI (שיהיה לוג שמראה מה קורה בנקודות זמן שונות)
Login במקום לבצע את כל הפעולות מה-CMDלבנות מסך שמראה את ה-
לשים SCANNER בסרבר שימשוך סיסמה כדי להיכנס לDB
הסרוור צריך לדעת מי מחובר\מנותק אליו בכל רגע נתון
המלצה מטירן: לעבוד עם OBJECT בניתוח של במקום STRING ולבצע את הניתוח על OBJECT

## Task2 - Man-Machine Interface
Links | משימה | בוצע? | קישורים
מטלה 2 - HTL + אב טיפוס | HTL | TRUE | מטלה 2 - HTL + אב טיפוס
מטלה 1 - ראיונות והסקת מסקנות | Low Level Prototype | TRUE | Figma - חלונות: ראשי, סטודנט מנחה
סיפור מטלה 1 | " | TRUE | חלון רכזת + מזכירה
מצגת HTL ממורקרת
מצגת LOW LEVEL PROTOTYPE ממורקרת | Window name: | Contains: | Details | Done?
Figma - חלונות: ראשי, סטודנט מנחה | Main Window | Option for each user to access their main profile * Student * Lecturer * Main Lecturer * Secretary |  | TRUE
חלון רכזת + מזכירה | Student Window | * Option to assign to a Lecturer (Table\ Drop down list) * Can filter lecturers by: Subject(Subject can be filter using: Point of interests OR Type of Technology) and lecturer's availability *! Option to find a partner to work with *! Has the option to contact with the lecturer in case they exist. *! Has the option to get a summary of the information about their project (Just a button) *! the student has a progress bar that helps them understand their current status.3 |  | TRUE
| Lecturer Window | * Can see how many projects + students are assigned to them * Student info per couple that are assigned to them. (such as: student names, student image, type of project they want to do) |  | TRUE
| Main Lecturer Window | * Table of Student assigned to the course: "Final Project". * In the same table, each couple of students has a checkbox that states if the couple is assigned to a project or not. And if the couple has decided on a subject for the project. |  | TRUE
| Secretary Window | * Table of Student assigned to the course: "Final Project". * In the same table, each couple of students has a checkbox that states if the couple is assigned to a project or not. And if the couple has decided on a subject for the project. | חלון מזכירה אחד לאחד כמו חלון רכזת הפרויקטים | TRUE
| Secretary Window | Add lecturer to the table |  | TRUE
FALSE
FALSE